## Sheet1
PROJECT TIMELINE
ACTIVITY | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Discussion & topic selection | bar: JUNE W1
Abstract submision | bar: JUNE W1 to JUNE W2
Requirement analysis | bar: JUNE W1 to JUNE W4
System design (diagrams) | bar: JUNE W4 to JULY W1
Phase 1 - game environment | bar: JULY W1 to JULY W2
Phase 2 - movement & collision | bar: JULY W2 to JULY W3
Phase 3 - GA + BFS map generation | bar: JULY W4 to AUGUST W1
Phase 4 - CA + A* map carving | bar: AUGUST W1 to AUGUST W2
Phase 5 - FSM monster + A* | bar: AUGUST W3 to AUGUST W4
Phase 6 - GA, rule-based decisions | bar: AUGUST W4 to SEPTEMBER W1
Phase 7 - combat, skills, inventory | bar: SEPTEMBER W1 to SEPTEMBER W2
Phase 8 - telementry | bar: SEPTEMBER W2 to SEPTEMBER W3
Testing & debugging | bar: SEPTEMBER W1 to SEPTEMBER W4
Documentation & repot | bar: JUNE W4 to SEPTEMBER W4
PROJECT TIMELINE
ACTIVITY | JUNE W1: JUNE; JULY W1: JULY; AUGUST W1: AUGUST; SEPTEMBER W1: SEPTEMBER
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Discussion & topic selection | bar: JUNE W1
Abstract submision | bar: JUNE W1 to JUNE W2
Requirement analysis | bar: JUNE W1 to JUNE W4
System design (diagrams) | bar: JUNE W4 to JULY W1
Phase 1 - game environment | bar: JULY W1 to JULY W2
Phase 2 - movement & collision | bar: JULY W2 to JULY W3
Phase 3 - GA + BFS map generation | bar: JULY W4 to AUGUST W1
Phase 4 - CA + A* map carving | bar: AUGUST W1 to AUGUST W2
Phase 5 - FSM monster + A* | bar: AUGUST W3 to AUGUST W4
Phase 6 - GA, rule-based decisions | bar: AUGUST W4 to SEPTEMBER W1
Phase 7 - combat, skills, inventory | bar: SEPTEMBER W1 to SEPTEMBER W2
Phase 8 - telementry | bar: SEPTEMBER W2 to SEPTEMBER W3
Testing & debugging | bar: JULY W3 to SEPTEMBER W4
Documentation & repot | bar: JUNE W4 to SEPTEMBER W4
PROJECT TIMELINE
ACTIVITY | JUNE W1: JUNE; JULY W1: JULY; AUGUST W1: AUGUST; SEPTEMBER W1: SEPTEMBER
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Discussion & topic selection | bar: JUNE W1
Abstract submision | bar: JUNE W1 to JUNE W2
Requirement analysis | bar: JUNE W1 to JUNE W4
System design (diagrams) | bar: JUNE W4 to JULY W1
Phase 1 - game environment | bar: JULY W1 to JULY W2
Phase 2 - movement & collision | bar: JULY W2 to JULY W3
Phase 3 - GA + BFS map generation | bar: JULY W4 to AUGUST W1
Phase 4 - CA + A* map carving | bar: AUGUST W1 to AUGUST W2
Phase 5 - FSM monster + A* | bar: AUGUST W3 to AUGUST W4
Phase 6 - GA, rule-based decisions | bar: AUGUST W4 to SEPTEMBER W1
Phase 7 - combat, skills, inventory | bar: SEPTEMBER W1 to SEPTEMBER W2
Phase 8 - telementry | bar: SEPTEMBER W2 to SEPTEMBER W3
Testing & debugging | bar: AUGUST W3 to SEPTEMBER W4
Documentation & repot | bar: JUNE W4 to SEPTEMBER W4